| # STEPS | # DATES |
| --- | --- |
| Minority Achievement Committee prepares proposed plan. | March – August 2001 |
| Proposed plan is presented to CUSF, AAAC, CUSP, and USM Student Council. | September – October 2001 |
| Minority Achievement Committee revises proposed plan. | October 2001 |
| BOR Education Policy Committee acts on proposed plan. | November 2001 |
| Full Board of Regents takes action on plan. | December 2001 |
| Formal dissemination of the plan to institutions | January 2002 |
| Institutions provide their plans and cost estimates to USM Office. | April 2002 |
| Minority Achievement Committee reviews institutional plans and provides feedback and technical assistance. | June 2002 |
| Institutions provide baseline data. | October 2002 |
| Institutions report annually after the baseline year. | End of October 2003 – and annually every October thereafter |
| Minority Achievement Committee reports to BOR Education Policy Committee on implementation of plans. | Spring, beginning in 2004 |